## Task Assignment
MSFincap — Phase 1 (PD Module) Task Assignment
Backend/Core Engine only
# | Layer / Module | Task / Responsibility | Assigned To | Notes
1 | Backend Layer | Set up Celery + Redis async job queue | Shashwat | All AI steps run here, stated interest
2 | Backend Layer | Define task contracts (task names, input/output schema) for all agents | Riddhi | Shared reference doc, agreed before both start
3 | Backend Layer | Set up FastAPI project structure, routers, and auth | Shared/Either | Thin routing layer
4 | Agent Layer | Integrate faster-whisper (self-hosted speech-to-text) | Riddhi | Feeds transcript downstream, pairs with queue ownership
5 | Agent Layer | Build Vision Extraction agent (LLM vision, constrained structured fields) | Riddhi | Requested "image model" work
6 | Agent Layer | Add YOLO object detection as supplementary signal alongside Vision Extraction | Riddhi | Generic object counts, cross-check only, not replacing vision-LLM
7 | Agent Layer | Build Classify + RAG agent (business category classification, gap analysis) | Shashwat | Text-based GenAI, generates constrained follow-ups
8 | Agent Layer | Build constrained follow-up question generator (question bank + few-shot depth limiting) | Shashwat | Ties to Classify + RAG output
9 | Agent Layer | CAM narrative generation (LLM writes Strengths/Weaknesses summary) | Shashwat | Uses same LLM interface
10 | External Services | Build swappable LLM API interface (Groq/Gemini, text + vision) | Shashwat | Both agents route through this one interface
11 | External Services | Integrate maps/geocoding API (reverse geocode, pincode match) | Riddhi | Feeds Land Valuation engine
12 | Database Layer | Design PostgreSQL schema (applications, pd_sessions, extracted_fields) | Shared, agreed together first | Both agents write here
13 | Database Layer | Set up pgvector + embeddings pipeline (sentence-transformers) | Shashwat | Feeds RAG retrieval
14 | Database Layer | Set up file storage (photos, audio, CAM PDFs) | Riddhi | Vision/speech agents write outputs here
15 | Reconciliation Layer | Build Land Valuation engine (three-source combination) | Riddhi | Reconciliation logic, not GenAI
16 | Reconciliation Layer | Build CAM Report Generator (assembles final PD report) | Shashwat | Pulls from both agents' outputs
17 | Cross-cutting | Build completion gate logic (blocks incomplete cases) | Riddhi | Reacts to job/queue completion events
18 | Cross-cutting | RAG knowledge base authoring coordination (20-25 profession docs) | Shashwat | Content work, not code — keep off pure engineering hour count
Task Count | Riddhi | Shashwat | Shared | Total
| 8 | 8 | 2 | 0